## Gantt Chart
	Thesis ConvNets: Speech Recognition					7%
	KU Leuven
	Matthijs Van keirsbilck		Monday, October 17, 2016

				39					40					41					42					43					44					45					46					47					48					49					50					51					52					01					02					03					04					05					06					07					08					09					10					11					12					13					14					15					16					17					18					19					20					21					22					23					24					25
WBS	Task Names	Resource Names	Start	Duration(h)	Hours completed	Hours Remaining	converted to # days	Days Completed	Finish	% Complete				Sep-16					Oct-16					Nov-16					Dec-16					Jan-17					Feb-17					Mar-17					Apr-17					May-17					Jun-17
	TOTAAL THESIS		20-Sep-2016	550	59	491	184		29-Mar-2017	7%				20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21

	Literatuurstudie algemeen		20-Sep-2016	15	15		5		26-Sep-2016	100%

	Software gedeelte		26-Sep-2016	375	44	331	125		29-Mar-2017	9%
	Inwerken in SW frameworks		26-Sep-2016	55	44	11	19		17-Oct-2016	79%
	installatie CUDA, Theano, IDE etc		26-Sep-2016	15	15	0	5	2	30-Sep-2016	100%
	opzetten Git, wiki, gantt chart		30-Sep-2016	10	10	0	4	3	05-Oct-2016	100%
	tutorial Neural Network from scratch WildML		05-Oct-2016	5	5	0	2	0	06-Oct-2016	100%
	Stanford course Neural Networks		06-Oct-2016	15	12	3	5		12-Oct-2016	80%
	WildML RNN, LSTM tutorial; experimenteren		12-Oct-2016	10	2	8	4		17-Oct-2016	20%

	Image Recognition (IR)		17-Oct-2016	115	0	115	39	0	05-Dec-2016	0%
	IR algemeen		17-Oct-2016	35	0	35	12		31-Oct-2016	0%
	Stanford course Convolutional NNs		17-Oct-2016	5		5	2		18-Oct-2016	0%
	literatuurstudie image recognition algemeen		18-Oct-2016	10		10	4		21-Oct-2016	0%
	implementeren image recognition algemeen		21-Oct-2016	20		20	7		31-Oct-2016	0%
	IR voor speech		31-Oct-2016	80	0	80			05-Dec-2016	0%
	Literatuurstudie IR voor speech		31-Oct-2016	20		20	7		08-Nov-2016	0%
	implementeren IR voor speech, statisch		08-Nov-2016	20		20	7		16-Nov-2016	0%
	implementeren IR voor speech, dynamisch		16-Nov-2016	40		40	14		05-Dec-2016	0%

	Speech Recognition (SR)		05-Dec-2016	55	0	55	19		27-Dec-2016	0%
	SR algemeen		05-Dec-2016	55	0	55	19		27-Dec-2016	0%
	literatuurstudie speech recognition		05-Dec-2016	20		20	7		13-Dec-2016	0%
	implementeren speech recognition letter		13-Dec-2016	15		15	5		19-Dec-2016	0%
	implementeren speech recognition woord		19-Dec-2016	10		10	4		22-Dec-2016	0%
	implementeren speech recognition zin		22-Dec-2016	10		10	4		27-Dec-2016	0%

	Gecombineerde SR en IR		27-Dec-2016	110	0	110	110		16-Mar-2017	0%
	Literatuurstudie		27-Dec-2016	20		20	7		04-Jan-2017	0%
	-> examens + lesvrije week
	in 2e semester meer tijd voor Thesis
	voorbeelden implementeren		15-Feb-2017	30		30	8		24-Feb-2017	0%
	implementeren eigen algoritmes		24-Feb-2017	60		60	15		16-Mar-2017	0%

	Schrijven thesis Software gedeelte		16-Mar-2017	40	0		10		29-Mar-2017	0%

	Hardware Gedeelte		29-Mar-2017	140	0	140	140		12-May-2017	0%
	Literatuurstudie		29-Mar-2017	40		40	10		11-Apr-2017	0%
	Mapping SW/HW		11-Apr-2017	80		80	20		08-May-2017	0%
	Schrijven Thesis HW gedeelte		08-May-2017	20		20	5		12-May-2017	0%

	Schrijven Thesis geheel		12-May-2017	20	0	20	5		18-May-2017	0%

		Gantt Chart Template V1.1
		Author: Fernando Ribeiro <pinguim.ribeiro@gmail.com>

		How To Use
		INSERT LINES:
		Insert the required number of lines: click the line number and drag down
		From the template, copy the required section or just one line
		INPUT DATA:
		WBS: to itemize the WBS copy and past the required level from the template
		Enter a Task and Resource Names
		Enter a [Start] date and a [Duration] (working days); The Due date is calculated and the task bar shows the task's duration on calendar.
		Or: Enter a [Start] and [Due] dates; The [Duration] (working days) is calculated and the task bar shows the task's duration on calendar.
		Enter a percentage in the [% Complete box]; the task bar shows a progress bar to indicate what percentage of the task is complete.
		Milestone: If you enter a start date without an end date, a milestone marker is displayed on the bar chart.
		In Categories tasks (level 1) Start, Due, Duration and Percentage Complete values are calculated; however they can be overwritten.

			Holidays